## Guide
Change log and request
• Every change to scope, time or cost gets logged here, assessed, and explicitly decided. Nothing absorbed quietly.
• Use the Request form tab to work up a single change in detail before it goes to the decision-maker.
• Impact is captured three ways — scope, time, cost — because a change rarely touches just one.
• Decision: Approved, Rejected or Deferred, with a name against it. 'The team decided' is not a decision.
• An approved change should update the plan, the baseline and the RAID log — not just this sheet.
A free tool from The Honest Programme · alkarakas.com

## Change log
ID | Date raised | Raised by | Change requested | Reason | Impact – scope | Impact – time | Impact – cost | Decision | Decided by | Status
CR-01 | 2026-06-09 | Client lead | Add single sign-on across all five units | Security policy updated mid-programme | New integration workstream | +2 weeks | +£18k | Approved | Sponsor | In progress
CR-02 | 2026-06-16 | Unit head | Custom report pack for Unit 3 | Local preference, not a requirement | Out of agreed scope | +1 week | +£6k | Rejected | Sponsor | Closed

## Request form
Change request
One change, worked up properly before it goes for a decision.
CHANGE ID | CR-__
DATE RAISED
RAISED BY
WHAT IS THE CHANGE?
WHY IS IT NEEDED?
WHAT HAPPENS IF WE DON'T?
IMPACT ON SCOPE
IMPACT ON TIMELINE
IMPACT ON COST
IMPACT ON RISK / QUALITY
OPTIONS (AND THE DO-NOTHING)
RECOMMENDATION
DECISION
DECIDED BY / DATE
A free tool from The Honest Programme · alkarakas.com