## Guide
Decision log
• A decision is only real once it is written down, owned, and dated. This is that record.
• The column that matters most is 'What we gave up' — every honest decision closes a door. Name it.
• Status: Proposed (not yet made), Decided (live), Superseded (replaced by a later decision), Reversed.
• Review by: set a date for decisions made on thin evidence, so you revisit them deliberately.
• Link a decision to the RAID item, change or assumption that triggered it where you can.
A free tool from The Honest Programme · alkarakas.com

## Decisions
ID | Date | Decision | Why (context) | Options considered | What we gave up | Decided by | Status | Review by | Notes
DEC-01 | 2026-06-08 | Migrate units in two waves, not a single big-bang cutover | Big-bang carried unacceptable rollback risk across five business units | (a) Single cutover (b) Two waves (c) Unit-by-unit over 6 months | Two extra weeks on the timeline, and a temporary dual-running cost | Sponsor (CIO) | Decided |  | Endorsed at SteerCo
DEC-02 | 2026-06-15 | Hold go-live until Finance data is signed off | Migrating unverified data would move the risk downstream, not remove it | (a) Proceed on current data (b) Hold for sign-off | The fixed go-live date, if sign-off slips again | PM | Proposed | 2026-06-26 | Revisit once D-01 closes