## Checklist
Right-sized governance checklist
Filter the 'Applies from' column to your engagement size. Everything at or below your size applies. Let complexity and risk override raw value.
Area | What good looks like | Applies from | Done? | Owner | Notes
Justification | A one-line reason it exists and a named beneficiary; stop if no longer true | Small (<£100k)
Justification | A light business case: cost, benefit, risk | Mid (£100k–0.5m)
Justification | Business case re-confirmed at each stage | Large (£0.5m–multi-£m)
Justification | Reference-class (outside-view) estimate and a benefits realisation plan | Major (multi-£m)
Ownership | One named owner accountable for the outcome | Small (<£100k)
Ownership | An engaged sponsor with sign-off authority | Mid (£100k–0.5m)
Ownership | Sponsor plus a small decision or steering group | Large (£0.5m–multi-£m)
Ownership | A programme board / SRO with delegated tolerances | Major (multi-£m)
Decisions | One honest go/no-go before money is committed | Small (<£100k)
Decisions | Start and close gates | Mid (£100k–0.5m)
Decisions | Stage gates with escalation when a tolerance is breached | Large (£0.5m–multi-£m)
Decisions | Staged gates plus independent assurance reviews | Major (multi-£m)
Scope and change | Scope written down in a sentence or two | Small (<£100k)
Scope and change | A simple change log | Mid (£100k–0.5m)
Scope and change | Change control with impact assessment | Large (£0.5m–multi-£m)
Scope and change | Baseline / configuration control and a formal change board | Major (multi-£m)
Risk | The top three risks written down, owner aware | Small (<£100k)
Risk | A RAID log, reviewed regularly | Mid (£100k–0.5m)
Risk | A risk register with named owners and mitigations | Large (£0.5m–multi-£m)
Risk | Quantified risk, contingency, and independent challenge | Major (multi-£m)
Reporting | Status visible to the owner, even one line | Small (<£100k)
Reporting | Lightweight status to the sponsor | Mid (£100k–0.5m)
Reporting | Structured reporting with clear escalation criteria | Large (£0.5m–multi-£m)
Reporting | A board dashboard, defined KPIs, and an audit trail | Major (multi-£m)
Closure | Confirm done; capture one lesson | Small (<£100k)
Closure | A short closure note | Mid (£100k–0.5m)
Closure | A closure report with lessons logged | Large (£0.5m–multi-£m)
Closure | A post-implementation and benefits review | Major (multi-£m)
A free tool from The Honest Programme · alkarakas.com

## Example (mid-size)
Right-sized governance checklist
Filter the 'Applies from' column to your engagement size. Everything at or below your size applies. Let complexity and risk override raw value.
Area | What good looks like | Applies from | Done? | Owner | Notes
Justification | A one-line reason it exists and a named beneficiary; stop if no longer true | Small (<£100k) | Yes | PM | On the one-pager
Justification | A light business case: cost, benefit, risk | Mid (£100k–0.5m) | Yes | Sponsor | Approved at kickoff
Justification | Business case re-confirmed at each stage | Large (£0.5m–multi-£m)
Justification | Reference-class (outside-view) estimate and a benefits realisation plan | Major (multi-£m)
Ownership | One named owner accountable for the outcome | Small (<£100k) | Yes | PM
Ownership | An engaged sponsor with sign-off authority | Mid (£100k–0.5m) | Yes | Sponsor
Ownership | Sponsor plus a small decision or steering group | Large (£0.5m–multi-£m)
Ownership | A programme board / SRO with delegated tolerances | Major (multi-£m)
Decisions | One honest go/no-go before money is committed | Small (<£100k) | Yes | Sponsor
Decisions | Start and close gates | Mid (£100k–0.5m) | In progress | PM | Start gate done
Decisions | Stage gates with escalation when a tolerance is breached | Large (£0.5m–multi-£m)
Decisions | Staged gates plus independent assurance reviews | Major (multi-£m)
Scope and change | Scope written down in a sentence or two | Small (<£100k) | Yes | PM
Scope and change | A simple change log | Mid (£100k–0.5m) | No | PM | Set up this week
Scope and change | Change control with impact assessment | Large (£0.5m–multi-£m)
Scope and change | Baseline / configuration control and a formal change board | Major (multi-£m)
Risk | The top three risks written down, owner aware | Small (<£100k) | Yes | PM | In the RAID log
Risk | A RAID log, reviewed regularly | Mid (£100k–0.5m) | Yes | PM | Reviewed weekly
Risk | A risk register with named owners and mitigations | Large (£0.5m–multi-£m) | Yes | PM
Risk | Quantified risk, contingency, and independent challenge | Major (multi-£m)
Reporting | Status visible to the owner, even one line | Small (<£100k) | Yes | PM
Reporting | Lightweight status to the sponsor | Mid (£100k–0.5m) | In progress | PM | First report Friday
Reporting | Structured reporting with clear escalation criteria | Large (£0.5m–multi-£m)
Reporting | A board dashboard, defined KPIs, and an audit trail | Major (multi-£m)
Closure | Confirm done; capture one lesson | Small (<£100k) | N/A |  | At closure
Closure | A short closure note | Mid (£100k–0.5m) | N/A |  | At closure
Closure | A closure report with lessons logged | Large (£0.5m–multi-£m)
Closure | A post-implementation and benefits review | Major (multi-£m)
A free tool from The Honest Programme · alkarakas.com