## Guide
Lessons learned log
• Capture lessons as they happen, not in a rushed session at closure when memory has faded.
• The honest format: what we expected, what actually happened, why, and the one thing we will do differently.
• A lesson is not learned until it changes something. 'Embedded' means a process, checklist or standard now reflects it.
• Tag the area (Planning, Scope, Risk, People, Vendor, Technical, Governance) so patterns surface over time.
• Good lessons are specific and blameless. 'Communicate better' is not a lesson; name the mechanism that failed.
A free tool from The Honest Programme · alkarakas.com

## Lessons
ID | Date | Area | What we expected | What actually happened | Why (root cause) | What we'll do differently | Owner | Status
L-01 | 2026-06-05 | Vendor | The vendor would confirm availability on request | Three weeks of silence; the integration slipped | No contractual response SLA; reliance on goodwill | Bake a response SLA into the next SoW; line up a backup vendor at kickoff | PM | Embedded
L-02 | 2026-06-14 | Scope | Change requests would be rare once scope was agreed | Steady stream of 'small' changes eroded the buffer | No change control in place early; changes absorbed informally | Stand up the change log on day one, not after the first overrun | PM | Open