Weekly status — [Programme name] — [week ending]

Honest by design. One page of boxes. It shows real delivery and names the gap, instead of a reassuring colour. A filled example follows.

THE ONE-LINE TRUTH Where we actually are this week.

DELIVERED THIS WEEK (DEMONSTRABLE) What can be seen, used or tested, not just worked on.

PLANNED NEXT WEEK The few things that matter most.

AGAINST THE PLAN On track, behind or ahead, by how much. If behind: what would have to be true to recover the date?

TOP RISKS AND ISSUES From the RAID log. The ones the sponsor needs to know.

DECISIONS NEEDED FROM THE SPONSOR OR CLIENT What you need, and by when.

WHAT I AM NOT SAYING OUT LOUD YET, AND SHOULD The honest line. Surface it here before it surfaces itself.

Worked example

THE ONE-LINE TRUTH Two days behind on the data migration, recoverable if Finance sign-off lands this week.

DELIVERED THIS WEEK (DEMONSTRABLE) Units 1–3 migrated to staging and validated. CI pipeline live. First end-to-end run green.

PLANNED NEXT WEEK Migrate units 4–5. Client UAT on units 1–3. Close out two priority issues.

AGAINST THE PLAN Behind by two days on migration. Recovers if the Finance export is signed off by Wed; otherwise cutover moves one week.

TOP RISKS AND ISSUES R-01 vendor availability (mitigating). I-01 test environment now resolved. D-01 Finance sign-off at risk.

DECISIONS NEEDED FROM THE SPONSOR OR CLIENT Confirm the Finance data owner by Wednesday. Approve the one-week contingency if sign-off slips.

WHAT I AM NOT SAYING OUT LOUD YET, AND SHOULD If Finance slips twice, the fixed go-live date is no longer credible and we should reset expectations now.