Post-implementation review — [Initiative]

The honest look back almost nobody ships. Did it deliver what it promised, and what would we do differently? Fill it in once the dust has settled. A worked example follows.

WHAT WE SET OUT TO DO The original objective and the success criteria, as written at the start — not as remembered now.

WHAT WE ACTUALLY DELIVERED The honest scope delivered, including what was cut or deferred.

BENEFITS: PROMISED VS REALISED For each benefit in the business case: was it realised, partly, or not? Use real numbers where you have them.

WHAT WORKED The decisions, practices and people that genuinely helped. Worth repeating.

WHAT DIDN'T The things that cost time, money or trust. Blameless, but specific.

WHAT WE'D DO DIFFERENTLY The few changes that would have made the biggest difference. Feed these into the lessons log.

OUTSTANDING RISKS AND HANDOVER What the receiving team needs to own from here, and any risk still live.

HONEST VERDICT In one line: was it worth it, and would we do it again the same way?

Worked example

WHAT WE SET OUT TO DO Consolidate five units onto one Azure tenancy with no loss of service, zero P1 incidents at cutover, each unit head signed off, by end of Q3.

WHAT WE ACTUALLY DELIVERED All five units live in two waves. The optional analytics pilot was deferred. Cutover completed two weeks later than the original date.

BENEFITS: PROMISED VS REALISED Support cost: down 28% (promised ~30%) — on track. Security baseline: fully realised. Same-day reporting: realised for four of five units; Unit 5 still partly manual.

WHAT WORKED Two-wave approach contained risk. Profiling the data before committing avoided a migration overrun. Weekly honest status kept the CIO ahead of bad news.

WHAT DIDN'T Vendor availability cost three weeks early on. Change control was set up too late, after the first scope creep had already eroded the buffer.

WHAT WE'D DO DIFFERENTLY Contract a response SLA and a backup vendor at kickoff. Stand up the change log on day one. Confirm SME availability in writing before mobilising.

OUTSTANDING RISKS AND HANDOVER Unit 5 manual reporting to be automated by the BAU team (owner named). Decommission of the last legacy tenancy scheduled for next month.

HONEST VERDICT Worth it — the recurring cost and security gap are gone. We would do it again, but with change control and vendor terms locked from the start.