## Guide
RACI matrix
• R = Responsible (does the work). A = Accountable (owns the outcome; exactly one per row).
• C = Consulted (two-way, before the work). I = Informed (one-way, after).
• The rule the 'Check' column enforces: every activity has exactly one A. No A means no owner; two means confusion.
• Keep it to the activities that actually need clarity. A RACI for everything is read by no one.
• Replace the role columns with your real roles before you share it.
A free tool from The Honest Programme · alkarakas.com

## RACI
Activity / deliverable | Sponsor | PM | Tech lead | Client lead | Delivery team | PMO | Check
Approve the business case | A | C | I | C | I | I
Define scope and Definition of Done | C | A | C | C | R | I
Maintain the RAID log | I | A | C | I | R | C
Run the cutover | I | A | R | C | R | I
Sign off go-live | A | R | C | C | I | I
Report status to the board | I | A | I | I | I | R