## Guide
RAID and Actions log
• One tab per log, each with the columns that log actually needs.
• Risks: things that might happen. Score = probability x impact. Response: Avoid, Reduce, Transfer or Accept.
• Assumptions: things taken as true. Each has a validate-by date; an invalid assumption becomes a risk or an issue.
• Issues: things that have happened and need resolving now.
• Dependencies: things you need from, or owe to, someone else.
• Actions: who is doing what by when.
• Dashboard and Matrix update themselves from the logs — read-only views, nothing to fill in.
• Cells with a due or target date turn red automatically when the date has passed and the item is still open.
• Dropdowns carry industry-standard options. Adapt the columns and options to your engagement.
A free tool from The Honest Programme · alkarakas.com

## Dashboard
RAID at a glance
Live counts from the logs. Nothing to fill in here.
Open risks | Status = Open on the Risks tab
Risks being mitigated
High-severity risks (score >= 15) | These need a named owner and a date
Open assumptions still to validate
Open issues | Open or in progress
Dependencies at risk or late
Open actions
Overdue items across all logs | Anything past its date and still open — chase these first
A free tool from The Honest Programme · alkarakas.com

## Matrix
Risk matrix (probability x impact)
How many live risks fall in each cell, pulled from the Risks tab. Red = act now.
Impact ->
|  | 1 | 2 | 3 | 4 | 5
Probability | 5
4
3
2
1
Score 15-25: act now
Score 8-12: manage
Score 1-6: monitor
A free tool from The Honest Programme · alkarakas.com

## Risks
ID | Risk (cause -> event -> effect) | Category | Probability | Impact | Score | Response | Owner | Raised | Target date | Mitigation / action | Status
R-01 | Vendor has not confirmed build-phase availability, so the integration could slip and delay go-live | Supplier | 4 Likely | 4 Major |  | Reduce | PM | 2026-06-01 | 2026-05-15 | Line up a second vendor; weekly check-in until confirmed | Open
R-02 | Scope is expanding faster than the team can absorb, risking budget overrun | Scope | 3 Possible | 4 Major |  | Reduce | Sponsor | 2026-06-10 | 2026-08-30 | Tighten change control; re-baseline at next gate | Mitigating

## Assumptions
ID | Assumption | Impact if false | Owner | Raised | Validate by | Status | Notes
A-01 | Client SMEs are available two days a week, as agreed in the SoW | Build slows and milestones slip | Client lead | 2026-06-01 | 2026-04-02 | Open | Chase written confirmation
A-02 | The legacy data is clean enough to migrate without remediation | Migration effort doubles | Data lead | 2026-06-05 | 2026-08-30 | Open | Sample and profile before committing

## Issues
ID | Issue | Impact | Priority | Owner | Raised | Target date | Resolution / action | Status
I-01 | Test environment not provisioned; blocking end-to-end testing | Testing cannot start | High | DevOps lead | 2026-06-12 | 2026-05-15 | Daily standup item; escalated to sponsor | Open

## Dependencies
ID | Dependency | Direction | Counterparty | Owner | Needed by | Status | Notes
D-01 | Sign-off on the data export from Finance before migration can run | Inbound | Finance team | PM | 2026-08-30 | At risk | No owner confirmed yet
D-02 | Security review of the integration by the client's InfoSec team | Inbound | Client InfoSec | Tech lead | 2026-05-15 | Late | Chase; blocking release

## Actions
ID | Action | Owner | Raised | Due | Priority | Status | Notes
AC-01 | Draft and circulate the Definition of Done for client sign-off | PM | 2026-06-10 | 2026-05-15 | High | In progress | Use the DoD template
AC-02 | Stand up the CI pipeline and seeded test database | DevOps lead | 2026-06-12 | 2026-09-20 | Medium | Open