## Guide
Stakeholder register and map
• Register every stakeholder who can affect, or is affected by, the programme. Then decide how to engage each.
• Influence and Interest are High / Medium / Low. The map plots them onto the classic four quadrants.
• High influence + high interest: manage closely. High influence + low interest: keep satisfied.
• Low influence + high interest: keep informed. Low influence + low interest: monitor.
• Stance is where they are now; Target is where you need them. The gap is your engagement job.
• The Map tab counts your stakeholders into each quadrant automatically — read-only.
A free tool from The Honest Programme · alkarakas.com

## Register
ID | Stakeholder | Role / organisation | Influence | Interest | Current stance | Target stance | Engagement strategy | Owner | Last contact
S-01 | Client CIO | Sponsor | High | High | Supporter | Champion | Weekly 1:1; bring decisions early with options | PM | 2026-06-18
S-02 | Finance Director | Data owner | High | Low | Neutral | Supporter | Keep satisfied; short, outcome-first updates | PM | 2026-06-10
S-03 | Unit heads (x5) | Affected users | Medium | High | Sceptic | Supporter | Keep informed; demo each wave; surface wins | Client lead | 2026-06-12
S-04 | InfoSec lead | Assurance | Medium | Medium | Blocker | Neutral | Engage now; agree review gates up front | Tech lead | 2026-05-15

## Map
Power / interest grid
Live counts from the Register. The strategy in each quadrant is the engagement default.
|  | Low interest | High interest
| High influence | Keep satisfied | Manage closely
| Low influence | Monitor | Keep informed
Count by quadrant
| Manage closely | High influence · high interest
| Keep satisfied | High influence · low interest
| Keep informed | Low influence · high interest
| Monitor | Low influence · low interest
A free tool from The Honest Programme · alkarakas.com