Team Charter — [Programme name]

One page the team agrees before the pressure starts. Fill in each box together and revisit it when things change. A worked example follows.

PURPOSE What this programme is for, in one sentence. What 'good' looks like at the end.

ROLES AND RESPONSIBILITIES Sponsor (accountable), delivery lead / PM, tech lead, client lead, and who owns what.

DECISION RIGHTS What the team decides itself, what needs the sponsor or client, and how we escalate (and how fast).

CADENCE Standup, sprint / iteration length, review or demo, retro, and reporting to the client.

WAYS OF WORKING Where the single source of truth lives, the agreed Definition of Done, and how we run the RAID log and who owns it.

COMMUNICATION: DO'S AND DON'TS How we communicate, with whom, and the promise that raising a problem is always safe.

Worked example

PURPOSE Migrate five business units onto one Azure tenancy with no loss of service. Good = all units live, zero priority-1 incidents at cutover, signed off by each unit head.

ROLES AND RESPONSIBILITIES Sponsor: client CIO (accountable). Delivery: Al (PM). Tech lead: J. Okafor. Client lead: per unit. Vendor coordination: PM.

DECISION RIGHTS Team decides sequencing and tooling. Sponsor decides scope and budget changes. Anything over 5 days' effort or affecting cutover dates escalates within 24 hours.

CADENCE Daily standup 09:30. Two-week sprints. Demo every second Thursday. Retro after each sprint. One-page status to the CIO every Friday.

WAYS OF WORKING Single backlog in Azure DevOps. Definition of Done agreed and pinned. RAID log reviewed weekly, owned by the PM, actions assigned with dates.

COMMUNICATION: DO'S AND DON'TS Do: bring problems early with options. Don't: surprise the client at SteerCo. Bad news goes to the CIO before it goes to the board.